## Slide 1
Darsi · free to copy for your school · Risk assessment: what could go wrong? · 1
Risk assessment: what could go wrong?
Cyber security · Level 4 · Lesson 2

## Slide 2
Darsi · free to copy for your school · Risk assessment: what could go wrong? · 2
Today we will
List the school’s information assets.
Score risks by likelihood and impact on a 3 × 3 grid.
Choose a control, an owner and a date for the top risks, in a simple register.

## Slide 3
Darsi · free to copy for your school · Risk assessment: what could go wrong? · 3
Score it, then fix it
Risk = likelihood × impact (1 to 9)
Fix the likely and serious first
Prevent, detect, recover
Every control has an owner and a date
Review the register every term

## Slide 4
Darsi · free to copy for your school · Risk assessment: what could go wrong? · 4
Risk hunt: our top three risks
Warm-up (5 min): Tell the power-cut story and ask what would have saved the exam papers.
Assets (7 min): List on the board what the school must protect.
Score (13 min): Groups write risks on slips and place them on the 3 × 3 grid.
Controls (10 min): For the top three, agree a control, an owner and a date.
Wrap-up (5 min): Copy the top three into the register and set a review date.
Draw a 3 × 3 grid on the board before the meeting: likelihood from 1 to 3 across, impact from 1 to 3 up, with the corner where 3 meets 3 marked “act now”. Prepare paper slips and tape, and invite the bursar and whoever looks after the computers.

## Slide 5
Darsi · free to copy for your school · Risk assessment: what could go wrong? · 5
Let’s discuss
Which of our risks is likely but dull, and still not fixed?
Which control could we put in place this week for free?
Who should keep the register, and when do we look at it again?

## Slide 6
Darsi · free to copy for your school · Risk assessment: what could go wrong? · 6
Exit ticket
Our highest risk, its score, and one control with an owner.